## Carta Gantt DS
Feriados | Actividades | Asginado a | Progreso | Inicio | Días | Final | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18 | 2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01
2025-04-18 | [6 empty] | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié | jue | vie | sáb | dom | lun | mar | mié
2025-04-19 | Fase de Análisis
2025-05-01 | Organización del equipo | PM - AP | 100% | 2025-03-25 | 1 | 2025-03-26 | bar: mar to mié; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
2025-05-21 | Definición de requerimientos funcionales y no funcionales | PM - AP | 100% | 2025-03-26 | 2 | 2025-03-27 | bar: mié to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
2025-06-20 | Fase de diseño | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
2025-06-29 | Captura de requerimientos específicos | PM - DEV - DBA - AP | 100% | 2025-03-31 | 2 | 2025-04-02 | bar: sáb to mié; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
2025-07-16 | Análisis de requerimientos | PM - DEV - DBA - AP | 100% | 2025-04-02 | 1 | 2025-04-03 | bar: sáb to dom; mié to jue; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
2001-09-18 | Diseño de la solución. Modelamientos | PM - DEV - DBA - AP | 100% | 2025-04-03 | 2 | 2025-04-07 | bar: sáb to dom; jue to lun; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Propuesta ERS | PM - DEV - DBA - AP | 85% | 2025-04-07 | 1 | 2025-04-08 | bar: sáb to dom; sáb to mar; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Plan de proyecto | PM - DEV - DBA - AP | 100% | 2025-04-08 | 1 | 2025-04-09 | bar: sáb to dom; sáb to dom; mar to mié; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
Fase de Implementación (Desarrollo - Alto Nivel) | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Implementación ambiente de desarrollo | PM - AP - DEV - DBA - UX - QA | 0% | 2025-04-09 | 1 | 2025-04-10 | bar: sáb to dom; sáb to dom; mié to jue; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| MDL.001: Gestión de Asistencia | PM - AP - DEV - DBA - UX - QA | 0% | 2025-04-10 | 9 | 2025-04-24 | bar: sáb to dom; sáb to dom; jue to jue; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| MDL.002: Gestión de Horas Extra | PM - AP - DEV - DBA - UX - QA | 0% | 2025-04-24 | 9 | 2025-05-08 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; jue to jue; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| MDL.003: Administración y Reportes | PM - AP - DEV - DBA - UX - QA | 0% | 2025-05-08 | 7 | 2025-05-19 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; jue to lun; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| MDL.004: Autenticación de Usuarios | PM - AP - DEV - DBA - UX - QA | 0% | 2025-05-19 | 8 | 2025-05-27 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to mar; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Integración del sistema | PM - DEV - QA | 0% | 2025-06-27 | 2 | 2025-06-29 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; mar to jue; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to lun; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
Fase de implementación y cierre | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Pruebas unitarias MDL.001 | PM - DEV - QA - DBA | 0% | 2025-06-29 | 4 | 2025-06-04 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; vie to jue; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Pruebas unitarias MDL.002 | PM - DEV - QA - DBA | 0% | 2025-06-04 | 5 | 2025-06-11 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to lun; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Pruebas unitarias MDL.003 | PM - DEV - QA - DBA | 0% | 2025-06-11 | 4 | 2025-06-18 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to lun; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Pruebas unitarias MDL.004 | PM - DEV - QA - DBA | 0% | 2025-06-18 | 5 | 2025-06-25 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Pruebas de integración | PM - DEV - QA - DBA | 0% | 2025-06-25 | 3 | 2025-06-30 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Migración del sistema a producción | PM - DEV - QA - DBA - UX | 0% | 2025-06-30 | 2 | 2025-07-02 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Pruebas de integración final | PM - DEV - QA - DBA - UX | 0% | 2025-07-02 | 1 | 2025-07-04 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Marcha blanca | PM - DEV | 0% | 2025-07-04 | 2 | 2025-07-08 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Capacitación | PM - DEV | 0% | 2025-07-08 | 1 | 2025-07-10 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
| Cierre de proyecto | PM - DEV | 0% | 2025-07-10 | 1 | 2025-07-12 | bar: sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; jue; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; vie to dom; sáb to dom; sáb to dom; sáb to dom; mié; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; sáb to dom; jue; sáb to dom; sáb to dom
INFORMACION CARTA GANTT
| ROL | SIGLA | NOMBRE | COSTO x HORA
| Jefe de Proyecto | PM | Vicente Ramirez | 13944.4444
| Analista Programador | AP | Vicente Ramirez | 9333.3333
| Analista Programador | AP | Cristian Parra | 9500
| Desarrollador o Programador | DEV | Maximiliano Mora | 10944.4444
| Analista de Base de Datos | DBA | Cristian Parra | 5250
| Tester o Analista de pruebas (QA) | QA | Maximiliano Diaz | 4958.3333
| Diseñador de Interfaz de Usuario (UI/UX) | UX Designer | Marcelo Muñoz | 4375
| TOTAL DIAS: |  |  | 74
TOTAL HORAS:
| COSTO PM: | 9035712
| COSTO AP: | $5.151.816
COSTO AP:
| COSTO DEV: | 6829056
| COSTO DBA: | 3192000
| COSTO QA: | 2657488
| COSTO UX: | 2135000
COSTO TOTAL:
Metodologia Usada:
1. Metodología de Gestión: El proyecto emplea una metodología Tradicional / Waterfall. Esto se evidencia por la planificación detallada y lineal de actividades con duraciones fijas, fases secuenciales implícitas por la progresión de roles en la tabla de actividades, y un seguimiento del progreso predefinido. Se diferencia de los enfoques ágiles por la falta de iteraciones, menor flexibilidad y ausencia de ceremonias ágiles. 2. Cálculo de Costos por Rol: Los costos se determinan en Pesos Chilenos ($) asumiendo 8 horas de trabajo por día por cada rol involucrado en una actividad. Costos por Hora de los Roles: PM: $13.944 AP: $9.333 DEV: $10.944 DBA: $5.250 QA: $4.958 UX Designer: $4.375 Proceso de Cálculo: Calcular el Costo por Día de cada rol (Costo por Hora × 8 horas/día). Sumar el Total de Días que cada rol participa en todas las actividades listadas. Multiplicar el Total de Días de un rol por su Costo por Día para obtener el Costo Total del Rol. Ejemplo PM: 81 días totales × 111.552/d a=$9.035.712. Costos Totales Finales por Rol: PM: $9.035.712 AP: $5.151.816 DEV: $6.829.056 DBA: $3.192.000 QA: $2.657.488 UX Designer: $2.135.000